## Sheet1
Week of 9/21 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Elevator Pitch Presentation, setting up of ReactJS, frontend development of login and registration forms, setting up client meeting | Andrew Jedlicka | 2h |  | .5h | 2.5h |  |  | .25h |  | front-end form: 25%
Elevator Pitch Presentation, presenting elevator pitch, backend development of login, configuration of backend connection to database, research on backend technologies | Blake Miller | 2.25h |  | .75h | 1.75h |  |  | .25h |  | backend plaintext registration: 80%
Elevator Pitch Presentation, Set up MySQL tables for user information | Shaun Trimm | 2h |  | .25h | .5h | .25h |  | .25h |  | database: 95%
Elevator Pitch Presentation, backend development of registration, connection of backend to database | Kevin Cao | 2h |  | .75h | 1.75h |  |  | .25h |  | backend plaintext registration: 80%