## Sheet1
Week of 9/28 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
frontend development of login, registration, forgot password, and reset password pages, facebook authorization and data fetching, duo front-end iframe | Andrew Jedlicka | 1h | 0.5h | 0.5h | 12h |  |  | 0.25h |  | all front end pages: 100%, facebook authorization and data: 100%, duo front-end iframe: 100%
Created login/registration feature, created password reset functionality, Duo implementation, team meetings | Blake Miller | 1 hr |  |  | 9 hrs |  |  |  |  | login/registration: 100%, password reset: 100%, duo login token authorization: 100%
Updated database file, created Duo account for application, Test Plan Document, team meetings | Shaun Trimm | .5hr |  | 1hr | 1hr |  |  |  |  | database file: 100%, duo account: 100%
Implemented password encryption, added paramaterized queries, created login/registration feature, moved application to Heroku, implemented token authorization, team meetings, implemented duo login token authorization | Kevin Cao | 1 hr |  | 2 hrs | 17 hrs |  |  | .25 hr |  | password encryption: 100%, parameterized queries: 100%, login/registration feature: 100%, Heroku deployment: 100%, token authorization: 100%, duo login token authorization: 100%, facebook oauth: 10%