## Sheet1
Week of 10/19 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Team and customer meetings, continued work on frontend widgets and gameplanning for sprint 3, worked a bit on suggestions for meeting from previous sprints | Andrew Jedlicka | 0.5hr | 0.5 hr |  |  |  |  | 0.5 hr | 0.5 hr | Widgets: 30%
Team meetings, customer meetings, backend widget implementation for assignments and grading | Blake Miller | 0.5hr | 0.5hr |  | 0.25hr |  |  | 0.25hr |  | User management widgets: 100%, Form validation for widgets: 100%
Team meetings, customer meetings, planning and research on possible widget changes and new widgets. | Shaun Trimm | 0.5hr | 0.5hr |  | 0.25hr |  |  | 0.5hr | 0.5hr | Widgets: 30%
Team meetings, added ability to add users to course, added ability to set the role of a given user, added form validation for widgets | Kevin Cao | 0.5 hr |  |  | 5 hr | .5 hr |  |  |  | User management widgets: 100%, Form validation for widgets: 100%