## Sheet1
Week of 10/12 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Finalized color scheme, created and implemented widgets, along with the drawer, navbar, and dashboard views | Andrew Jedlicka | 0.5 hr | 0.5 hr |  | 19 hr | 1 hr |  | 0.5 hr | 1 hr | Dashboard View: 80%, Login and Registration: 100%, Widgets: 90%
Created backend get requests for Assignments, Announcements, Courses, roles, and helped with creation of individual widget backend implementation, Helped create tables for get requests and endpoints | Blake Miller | 0.5hr | 0.5hr |  | 8 hr | 0.5hr |  |  |  | Backend Get Requests: 100%
Created Widgets for the Dashboard, Test Plan Document, team meetings | Shaun Trimm | 0.5hr | 0.5hr | 0.5hr | 6 hr | 1 hr |  |  |  | Widgets 90%, Test Plan Document 100%
Created endpoints for backend, created queries for retrieving announcements/assignments per class, created queries for accessing assignments for specific dates, added functionality to create announcements, Deployed to Heroku and set up database for demo, created documents for API reference | Kevin Cao | 0.5 hr | 0.5 hr | 1 hr | 13 hr | 2 hr |  |  |  | Backend Endpoints for Announcement/Assignment Retrieval: 100%, Connecting calendar to backend: 100%