## Sheet1
Week of 10/5 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Wrapped up changes to login and registration pages, started work on drawer, navbar, and widgets on dashboard view | Andrew Jedlicka | 1hr | 0.5hr | 2hr | 1hr |  |  | 0.25hr |  | Dashboard View: 15%
Worked on design of SQL queries, attended meetings for front-end and back-end | Blake Miller | 1 hr |  | 2hr | [5 empty] | Queries: 100%
Designed tables for the SQL database, discussed dashboard layout, added alerts/handlers for HTTP status codes, discussed widget design and use | Shaun Trimm | 1 hr |  | 1.5hr | .5hr | .25hr |  |  |  | SQL database: 95%, widgets : 10%, alerts/handlers for HTTP status codes: 80%
discussed design plan for dashboard, created spreadsheets containing API reference, including HTTP status codes, and HTTP endpoints | Kevin Cao | 1 hr |  | 1 hr | .25 hr |  |  | .25 hr |  | design plan: 50%, api reference: 100%