## Sheet1
Week of 10/26 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Created assignment, submission, and grade views for the student for the frontend and assisted with the create assignment widget and calendar view. Cleaned up the login and previous widgets. Created front end media player. Met with team several times | Andrew Jedlicka | 1 hr | 0.5 hr | 0.5 hr | 8 hr |  |  |  |  | Front end student grading and submissions: 90% Lecture views: 100%
Helped with AS3 integration, Created Get/POST requests for grades, assisted in redesigning grades infrastructure in tables, wrote endpoints for assignments and grades | Blake Miller | 2 hr |  | 1 hr | 4 hrs |  |  |  |  | GET/POST for grades: 80%. Writing endpoints 100%
Created widgets and views for the frontend including, the unapproved files widget, the instructor assignment view, submissions and grade view for instructors, and the create assignment widget. Modified files and lecture videos tabs to check for roles in order to allow instructor upload. Test Plan Document. Team meetings | Shaun Trimm | .5hr |  | 1.5hr | 7hrs | 1hr |  |  |  | Widgets and front end views relating to files and grades 90%. Test Plan Document 100%
Connected backend to AWS S3, created GET/POST endpoints for course files, created POST endpoint for submissions, added logout functionality, created GET endpoint for retrieving students of a course, created GET/POST endpoints for retrieving submissions, created GET/POST endpoints for course videos, created GET/POST endpoints for assignment files, designed file structure for s3, created detailed endpoints descriptions and object return types for frontend use | Kevin Cao | 2 hr |  | 1 hr | 10 hrs |  |  |  |  | All necessary endpoints: 100%