## Sheet1
Fortnight of 11/22 |  | Man-Hours Worked This Fortnight (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Worked on frontend of chat, landing page, default widgets, and dark mode implementation | Andrew Jedlicka | 0.5 hr | 1 hr | 2 hr | 18 hr | 2 hr |  | 0.5 hr |  | frontend chat: 100%, landing page: 100%, default widgets: 95%, dark mode: 100%
Experimented with and solidified colorschemes, created images and researched solutions for landing page, assisted in creating default widget states, created and implemented new icons, assisted in aesthetic changes to color and font | Blake Miller | 1 hr |  | 5 hr | 5 hr |  |  | 4 hr |  | Colorscheme 100%, images 90%, icons 100%, aesthetic 90%
Worked on finishing the UnapprovedFiles widget, InstructorAssignment view, StudentGrade view, Average grade per assignment, and the overall grading functionality, Test Plan Document | Shaun Trimm |  |  | 1 hr | 13 hr | 4hr |  |  |  | UnapprovedFiles100%, InstructorAssignment view 100%, StudentGrade view 100%, AverageGrade per Assignment 75%, Grading 100%, Test Plan Document 100%
Added tables in database for chat, added sockets for real-time chat, built frontend for chat, integrate backend and frontend together for chat, added online status and is typing chat features, added editable markdown syllabus to course homepage, finished chat/files/syllabus/grading endpoints, integrated syllabus frontend and backend | Kevin Cao | 1 hr | 1 hr | 6 hr | 30 hr | 6 hr | 1 hr |  |  | 100% chat, 100% syllabus, 100% grade endpoints, 100% file approval endpoints