## Sheet1
Week of 11/1 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Demoed project and completed minor UI updates, met with customer to discuss demo and sprint | Andrew Jedlicka | 0.5 hr | 0.5 hr |  | 0.5 hr |  |  | 0.5 hr
Took notes during project demo, recorded UI updates in JIRA, met with customer to discuss demo and sprint | Blake Miller | 1 hr | 1 hr
Updated and tested the Create Assignment widget, team and customer meetings | Shaun Trimm | .0.5 hr | 0.5 hr |  | 4 hr | 1 hr |  |  |  | Create Assignment widget: 95%
Completed endpoints for approved/unapproved files, completed endpoints for creating assignments, designed plan for implementation of search | Kevin Cao | .5 hr |  | .5 hr | 2 hr | 1 hr |  |  |  | endpoints for files: 100%, endpoints for assignments: 100%