## Sheet1
Week of 11/1 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Worked on frontend of search widget and search on class panels. Implemented endpoints to complete searching functionality | Andrew Jedlicka | 0.25 hrs | 0.25 hrs | 0.5 hrs | 12 hrs |  |  |  |  | Frontend search: 90%
Minor UX improvements, research into image integration for sidebar and courses, system design document | Blake Miller | 1 hr |  | 1 hr | 1 hr |  |  |  |  | UX: 40%, system design Doc: 100%
Finished the CreateAssignment widget, implemented grading functionality, UnapprovedFiles widget, Instructor Assignment view, Test Plan Document | Shaun Trimm |  |  | 1hr | 8hr | 1hr |  |  |  | CreateAssignmentWidget 100%, Grading 100%, UnapprovedFiles 80%, InstructorAssignment view 90%, Test Plan Document 100%
Added search endpoints, adjusted file endpoints as per frontend requirements, worked on frontend integration with file requests | Kevin Cao | .5 hr |  | .5 hr | 6 hr | .5 hr |  |  |  | search endpoints: 100%, file endpoints: 100%, frontend integration: 80%