## Sheet1
Week of 9/14 |  | Man-Hours Worked This Week (Round to nearest .25 hours)
Project Function, Deliverable, Component Name | Responsible Person | Project Plan | Req. Dev. | Design | Implementation | Test | Delivery | Project Management | Change Control | Estimated Component % Complete
Setup Github Repository | Andrew Jedlicka | [6 empty] | 0.25h |  | 100%
Initial User Stories on Jira | Kevin Cao |  | 0.5h | [6 empty] | 100%
Slack Workspace | Andrew Jedlicka | [6 empty] | 0.25h |  | 100%
Project Plan | Kevin Cao | 2h | [7 empty] | 100%
Project Plan | Andrew Jedlicka | 2h | [7 empty] | 100%
Project Plan | Shaun Trimm | 2h | [7 empty] | 100%
Project Plan | Blake Miller | 2h | [7 empty] | 100%
Customer Meeting Minutes | Andrew Jedlicka |  | 0.5h | [6 empty] | 100%
Weekly Status Report | Andrew Jedlicka | [6 empty] | 0.5h |  | 100%
Weekly Status Report | Shaun Trimm | [6 empty] | 0.5h |  | 100%
Weekly Status Report | Kevin Cao | [6 empty] | 0.5h |  | 100%
Scheduling Meetings | Kevin Cao | [6 empty] | 0.25h |  | 100%